## Slide 1: Digital Derivative Example: Clinical Case Email
Request: Brand Team Shares Need w/ MCE HUB & MCE PM (Jeremy) & Provides Following Information: Previous Piece Veeva #, Timeline/In Market Date, Cost Center / IO, Claims, Marked up pdf w/ changes/updates needed; Measurement defined by MCE HUB
IT/3rd Party Involvement: Jeremy reaches out to IT and any needed 3rd parties
Hibbert: IT initiates contact w/ Hibbert if needed
Veeva Initiation: Jeremy (MCE PM) initiates project in Veeva, enters meta-data. Jeremy is Project Owner in Veeva
Kick-off: Jeremy Schedules kick off, brand associate completes risk assessment; Kick off occurs (Jeremy, Director, MIA, Associate optional, IT (Bill) optional)
File Hand Off: Jeremy requests files from agency that led prior piece; IT already has code for sites; Agency will send PSD files if needed (PSD not final, code is)
Piece Creation: Jeremy works with IT (Bill); IT creates the piece, develops w/ Development Pool, and pulls in Hibbert; MCE connects w/ IT (Bill) on CTA and measurement coding / tagging
Piece Review: IT (Bill) reaches out to Jeremy and Brand team to review the piece prior to PCA
PCA Submission: Jeremy submits piece to PCA
PCA Comments / Attendance: Brand assumes role, reviews comments, etc.; Brand attends live if needed, IT (Bill) live if needed
Deployment: IT implements w/ Hibbert (test blast, deployment, etc.)

## Slide 2: Digital New Tactic Example: Phase 10 Site
Request: Brand Team Shares Need w/ MCE HUB & MCE PM (Jeremy); Timeline & Measurement defined by MCE HUB (w/ brand, IT, agency)
IT/3rd Party Involvement: Jeremy reaches out to IT and any needed 3rd parties
Creative Development: Agency owns creative
Veeva Initiation: Jeremy (MCE PM) initiates project in Veeva, enters meta-data. Jeremy is Project Owner in Veeva
Kick-off: Jeremy Schedules kick off, brand associate completes risk assessment; Kick off occurs (Jeremy, Director, MIA, Associate optional, IT (Bill) optional)
PCA Consult: Agency takes flats w/ wireframes, creative, etc.; UX involved; IT already has code for sites
Piece Creation: Jeremy works with IT (Bill); IT creates the piece, develops w/ Development Pool including UX involvement (Terry), and pulls in Hibbert; MCE connects w/ IT (Bill) on CTA and measurement coding / tagging
Piece Review: IT (Bill) reaches out to Jeremy and Brand team to review the piece prior to PCA
PCA Submission: Jeremy submits piece to PCA
PCA Comments / Attendance: Brand assumes role, reviews comments, etc.; Brand attends live if needed, IT (Bill) live if needed
Deployment: IT implements & site goes live; Jeremy confirms 2253 submission